## Master Sheet
Product | Phase | Description | Detailed Description | Time Frame | Remarks(if any challenges faced and comments) | From whom support is taken | People met for task
| Data Procurement | Receive Data from Edge and Incubator Program | Meet Edge and Incubator Team | 1 week(20th to 25th June) | Message from Aravind Sir approved on 24th June |  | Azhar, Kedar and Edge Team , Amrut
| Data Cleaning | create dataset according to our need | selecting similar industries making data suitable for our requirements | 3 days(27th to 30th June) | Would be required to look at the available data from intenrnal DS while coming to a conclusion about definition of success |  | met Benjamin sir,
Revenue Estimator Model | Data analysis | analyse the data to make sense of the issue at hand | necessary to make the model fit to our requirements | 3 days(30th June to 4th July)
| Data Engineering | Transforming the data to best suit the model |  | 3 days(5th July to 8th July)
| Model Making | Making the model | Creating the model using scikitlearn, | 4 days(9th July to 13th July)
| Testing | Testing the model and fine tuning it |  | 2 days (14th July to 16th July)